## Slide 1: Project Management – Professional Development Series
Facilities and Campus Services
Engineering and Project Management
April 14, 2020

## Slide 2: Pooled Contingency
Why
  Issue
  Goal
What
  Historical Data
  Recommendations
How
  Budgeting
  Approvals
Notes: Memo – Signed Back in January 2020
- Planned Maintenance Projects will utilize a pooled contingency

## Slide 3: Why -
Issue:
Unused Contingency Funds tied up for the duration of a project
Goal:
Ensure that Planned Maintenance funds are spent in a timely manner.
Historical Data: Planned Maintenance
  Average Contingency 8.5%
  37% spent on average (~ 3.5%)

## Slide 4: What -
Recommendations:
Projects Under $2M
  3.5% Contingency Budgeted
Establish Pooled Contingency
  Pool to be Tracked & Managed
  Requests for funds via signature PAR
  Gibbs & Barton delegated Transaction Authority up $100k
Notes: Audience:
Who is this for?
Stakeholders, Project Directors, and Administration
Goal of the Project Status Update is to fully inform the project directors / Executives and Stakeholders of your project's status and overall direction without having to get involved themselves.
Directors/Stakeholders should be able to read the project status without having to reach out to the PM directly to find out where things are. A project manager is to create clarity from confusion for the project team and for management. Essentially, the task of a project status update is one of analysis and communication.

## Slide 5: How -
Leverage PM Tool eBuilder
Details Page
  Is project eligible
Budgets
  Establishing your Project Budget
Approval Process & Cornell Policy
  eBuilder Process TBD
    Revised Pooled Contingency PAR
    Pooled Contingency Budget Change?
Notes: Audience:
Who is this for?
Stakeholders, Project Directors, and Administration
Goal of the Project Status Update is to fully inform the project directors / Executives and Stakeholders of your project's status and overall direction without having to get involved themselves.
Directors/Stakeholders should be able to read the project status without having to reach out to the PM directly to find out where things are. A project manager is to create clarity from confusion for the project team and for management. Essentially, the task of a project status update is one of analysis and communication.