## Slide 1
*As you sign on, please send your net ID to Paula Slocum via a private chat so she can mark you as attended

## Slide 2
Project Management – Professional Development Series
Facilities and Campus Services Engineering and Project Management
September 24, 2020

## Slide 3: Willard Straight 414
FE Minute: Temporary Ventilation

## Slide 4: Willard Straight Memorial Room
Project Overview
  Project Manager - Elisabete Godden
  Designers – Steve Beyer and Scott Burke
  Construction Manager – Pat Conrad
Schedule
20 days from project introduction to final delivery
Scope
Installation of temporary ventilation systems and
related equipment at various spaces for use during
the COVID Pandemic to increase air flow
(in classrooms without mechanical ventilation)
Budget
$100,000~
FE Minute: Temporary Ventilation
4

## Slide 5
Contract
Stand Alone Contract for T&M with W L Klein
Goals
30 min. max PM response time to campus partners and team members
24 hrs notice to building occupants of access requirements to their facilities
Committed to 50 spaces designed and installed in 20 days
Execution
Daily core team check in and constant communication with contractors
Daily status updates to Stakeholders team with succinct information
  Number of spaces flagged for ventilation on OUR (central registrar)
  Number of spaces designed
  Number of spaces installed
  Number of working days left to fall classes 2020
5
FE Minute: Temporary Ventilation

## Slide 6
Risks and Challenges
List of classrooms needing temporary ventilation was not yet complete
Had to help campus partners determine where mechanical ventilation was not available or not functioning
Class list was a moving target, some spaces were still not laid out for COVID Occupancy for design calculations
Setting up the entire project in 24hrs (PIR, eBuilder, Self-Pricing Invitation to Bid, and Contract) so materials could be ordered ASAP
Quick decisions about ordering materials prior to number of spaces known or design complete
Hire contractor and order materials prior to design documents due to potential equipment shortages and delays in delivery
Accessing spaces during a pandemic on short notice
6
FE Minute: Temporary Ventilation

## Slide 7
System Design Concept
Design consisted of inline fans, window panels, window vents, insulated flexible ductwork and fan speed controllers
Met NYS Mechanical Code minimum (ASHRAE 62.1)
Maintained building pressurization
Intake and Exhaust Vent locations carefully considered
Supply air to front of classroom where possible
Install timers to reduce energy use when ventilation is not needed
FE Minute: Temporary Ventilation

## Slide 8: Plant Sciences G22
FE Minute: Temporary Ventilation
Design Diagram Example

## Slide 9
FAN
CONTROLLER
FE Minute: Temporary Ventilation
Typical Installation Example (Interior)
Morill 111

## Slide 10: Hollister Hall
Typical Installation Example (Exterior)
FE Minute: Temporary Ventilation
EXHAUST VENT
INTAKE VENT

## Slide 11: Sage Chapel
Unusual Installation Example
FE Minute: Temporary Ventilation
Notes: Exhaust Plenum Box Thank Steve Beyers

## Slide 12
Lessons Learned, Successes and Outcomes
Timers in fan controller were not reoccurring
Its best to determine and test controls upfront
Timely and clear communication is key
Challenges need to be addressed ASAP
Making decisions based on best-practices is ok
Think ahead and prepare for plan b, c, d…
Surplus materials can be used for replacements
When given the opportunity exceed expectations:
This contract is also helping SCL install temporary ventilation at an additional 160 spaces
FE Minute: Temporary Ventilation
Notes: Thanks John Bell and Erich Riecard

## Slide 13
Next Steps, Looking Ahead
Prepare for cold season and brainstorm air tempering with campus partners
Consider various solutions for different spaces and uses
Test installs in SCL lounge spaces that are used 24/7
FE Minute: Temporary Ventilation
Notes: Thank Vince and Mechanical Team Thank Erich Eschellman

## Slide 14
Thank You
Questions?