## Slide 1: eB Minute
December 2021
Modified per the discussion that took place in the PMPD zoom meeting on 12/15/2021

## Slide 2
Preferred PCO Reason Codes
Only Three Reason Codes Expected To Be Used For All PCOs:
Error / Omission
Program Add/Change
Unforeseen Condition
Project Managers and Project Directors should be reviewing the selected reason code on all PCOs to verify or correct so that the appropriate reason code is used

## Slide 3
Never Used PCO Reason Codes
Do not use these reason codes for PCOs:
Amendment (Not for Construction Contracts)
Other (Administrators only)
PO Change (Purchase Orders only not Construction Contracts)
SOV Breakout (Schedule of Values process only)
Value Engineering (Post Bid Activity not after Contract Award)

## Slide 4
Rarely Used PCO Reason Codes
These reason codes may be used on rare occasions, special circumstances, or GMC Contracts - Consult your Director and/or Contracts Office first
Allowance Adjustment (Only when change to an Existing Allowance)
GMC Contingency (Only GMC Contingency Use)
Retention Reduction (Used to Reduce the % of Retainage held on entire contract)
Savings/Settlement (Only for Shared Savings at end of project - typically GMC)
Time Extension (Only for No Cost Time Extension - typically Campus Let)
*Code Modification (AHJ Directed Modifications) *Post-presentation edit

## Slide 5
eBuilder Reminder
“eB administrators will need to make the corrections on completed PCOs, where “do not use” reason codes have been used. We will be contracting Project Managers in the new year to request assistance with identifying the correct/preferred reason codes.”
Contact us by our group email address:
e-buildergroup@cornell.edu

## Slide 6: Questions?