## Slide 1
Project Management – Professional Development Series
Facilities and Campus Services Engineering and Project Management
February 28, 2022
Notes: Reminder about March PMPD

## Slide 2: Contract Processes in eBuilder
Best Practices
eBuilder Process Attachments
Notes: Attachments to include in the BP, CRP, CAA, CO, TA, IDIQ and PA processes in eBuilder to keep them routing forward.

## Slide 3: Purpose
For auditing purposes, each eBuilder process requires the appropriate documentation attached to show why and how the work was requested.
Notes: Tip: Assist in the naming convention with Contractors submissions/scanned items.

## Slide 4: Bid Preparation (BP)
Front End Word Documents
Technical Specifications and Drawings
Asbestos Reports
OPC/Estimate
Electronic Bid Scope
Other (SWPPP, Geotechnical, Surveys, etc.)
For Campus Let – DOB 1184
Notes: Front ends 01-07
Campus Let – Use Campus Let Front Ends

## Slide 5: Design Agreements (CRP)
RFP
RFI Log
Selected Consultant’s Proposal
Fee Breakdown (Rates and Phases)
Contract Acknowledgment Form
Any revised information (schedule, etc.)
Single Source Justification
Notes: Found in the 06.01 eBuilder documents folder
(Final versions sent, no drafts) – we do not need Design Agreement attached
Be sure to verify and update RFP dates of phases if necessary
For revised information note which to use

## Slide 6: Short Form Construction Agreement (CRP)
Invitation/Email
Scope of Work
Low Bid Proposal
Addendums/RFIs
Bid sheet
Single Source Justification, if applicable
Note: if Self Pricing, remember that all documentation and correspondence (drawings, specs, sketches, asbestos reports, RFIs, etc.) are copied to FC email
Notes: Be sure to add the amount in the 01 Construction line.

## Slide 7: Construction Agreements (CRP)
Bid sheet
Bid Proposal Certification / Bid Form (if Campus Let)
Advise on Selected/Rejected Alternates
Bid Bonds
Scope Validation
Post Bid Bulletin, if applicable

## Slide 8: Amendments (CAA)
Need to provide how the work was requested (minutes, Scope of Work, email) or add an eB Comment
Consultant’s Proposal
Fee Breakdown (Rates & Hours by Phase)
Revised Schedule, if applicable
Notes: Also, always the “Add All Existing Items” button in the Commitment Change section, before noting additional funding. Do not create new lines for existing lines. Amounts should match the Fee breakdown.

## Slide 9: Change Orders (CO)
Subcontractors pricing (materials & labor)
Consultant / Field directives (ASI, Bulletins, emails, etc.)
Campus Let Projects that require OSC approval need additional attachments
Note: on PCOs include the following:
  Detailed Description: clearly define the work – what and why is it needed
  Justification: state why the work is required and approve the pricing / markups
Notes: PMs are responsible for reviewing pricing / markups
Campus Let projects emphasize this

## Slide 10: Task Authorizations (TA)
IDIQ TAs need to attach RFP and Proposal with standard rates/spreadsheet
Need to attach the referenced WO or provide the Scope of Work issued

## Slide 11: Payment Applications (PA)
1st payments need the Contractors Waste Material Disposal Forms
All TA payments need to attach an invoice or their blanket spreadsheet
Contractors TAs need a Notarized Waiver of Lien
Prevailing Wage Rate projects require Certified Payroll in the field provided (not in attachments tab)
Contractors’ Final payments requires a notarized Final Release of Lien
Projects with subcontractors need their Final Release of Liens totaling less than GC’s final payment amount due

## Slide 12
Working together to reduce revisions and make the process move forward in a timely manner.

## Slide 13: Questions?