## Slide 1: Facilities Contracts
Change Order (PCO)
Requirements
April 2023

## Slide 2: Required Backup
How the work was requested needs to be a clear and concise explanation.
Always attach the Contractors Change Order Request form (COR)
All relevant BA/ASI/RFI/emails/etc. need to be attached to the PCO process.
When requesting work verbally a confirmation email should be sent to vendor to confirm.

## Slide 3: Justification vs. Description of Work
Justification section:
  Describe what work was performed clearly referencing any BA/ASI/etc.
  It should answer “Why did we have to do this”
Change Order Description:
  This language becomes part of the Contract via the CO.
  Needs to be clear – “what they are doing and where”, “how it is being done” and “per ASI/BA/etc.”

## Slide 4: Review your PCO’s
Double check dollar value
  The COR should have been reviewed for accuracy (OH&P, Bond, etc.)
Make sure COR form is filled out all required backup is attached for both Prime and Subs.
Provide an updated Completion date, if applicable
  Campus Let Projects need to have this in the PCO or a justification memo is required.

## Slide 5: Reminders
Use the Comments Tab to advise Contracts of any additional information
Check your email and queue for any Request Comments
Allowances need to be reconciled by the end of the Project
CO’s due to supply chain, etc. will not be processed

## Slide 6: Questions?