## Slide 1
Contracts Housekeeping
(How to speed things up)

## Slide 2: Summer Staffing
If you are out for more than one day, please put an Out of Office message up with who to contact in your absence
Contracts Office: open positions, leaves, and vacations
If you are emailing one of the FC staff members, please copy the FC Mailbox

## Slide 3: Cornell Bidding Calendar
Shared Outlook calendar updated weekly which shows the following:
  Documents to Contracts date – Pulled from the project eBuilder schedule populated by the PM
  Last Questions Due, Final Addendum, and Bid Opening are Populated by Contracts once project is out for bid
  Key personnel out of office

## Slide 4: Cornell Bidding Calendar
Guidance Document
  https://app.e-builder.net/public/fileview_fileview_act.aspx?portaltype=7&o=%7b92dcd545-694f-4862-860a-7b6eaaf4a3e1%7d
Monthly meeting with FCS PM Directors and UFD’s to discuss upcoming bids, confirm dates, prioritize project deliverables, and strategize bid timing

## Slide 5: Bidding Strategy
Recent and Current Bidding Climate:
  High bids, low bidder participation, Multiple projects with no bidders
  Small pool of contractors to handle large workload/labor strained
  High volume of work in the Ithaca area
  20 out of 30 bids in 2023 were over budget
  Recent Contractor Feedback – Too busy, no subs available to meet schedule, project timing, booked until Fall.
  Need to put projects out to bid early and not wait

## Slide 6: Bidding Strategy
Bid Dates
  T, W, Th are the best bidding days
  No bids scheduled Friday after 2:00PM
  Don’t bid multiple projects for the same trade on the same day, or week if possible
  Maximum of 2 bids per day
  Communicate early when planning for potential bid package deliverables and prep 7-10 days.

## Slide 7: Bidding Strategy
There is no straight forward approach, every project is unique
Include as many qualified contractors as possible, don’t limit yourself on bid day
Understand contractors are building in costs to cover unknowns (market conditions, supply chain, and labor issues.)
Check your OPC’s, use past bid data for reference (bid tabulation report)

## Slide 8: Bidding Strategy
Be sure you have the right delivery method, who should be the prime.
Consider pre-purchasing long lead items when possible (access control hardware, HVAC Equipment, lab casework, electrical gear, wood door leafs, etc.)
Give the contractor options by keeping specifications open for competition when possible

## Slide 9: Bidding Strategy
Avoid late Spring/Early Summer bids, Refer to the bidding calendar to select optimal times to bid your project
Keep Holidays (Campus and National) and events in mind. (Slope Day, Reunion, Columbus Day etc.)
Consider flexible on-site start dates, standard is 14 days after NTP – Better GC efficiency
Understand project complexities (limited shutdowns, winter break work) and be clear about special conditions.

## Slide 10: CRP’s
Please use the “Scope of Work” section to communicate changes
  Updating the completion date from the bid docs, put in a comment
  Notate if you are accepting/not accepting any Alternates
For Design, make sure your schedule from the RFP is still accurate, if not attach an updated schedule to the process
If the contract has been delayed past the 90 day price hold, request and attach a letter from the Contractor confirming that they are holding the bid price

## Slide 11: Contract Amendments
All amendments need to attach something showing how the additional work was requested
  (Email, meeting minutes, Scope of Work, etc.)
  If it was a verbal communication, put a comment in the process stating so.
For the “Commitment Change Items”, always click on the “Add All Existing Items” and add the request to the existing committed lines, don’t make new ones.

## Slide 12: Change Orders
When you have between 3 - 8 PCO’s you should create a Change Order, no more than 10 please
Do not submit CO’s or CAA’s before the previous one is fully executed as the totals will not match in eBuilder
Allowances may only be used for their intended purpose
Make sure you reconcile your Allowances via a change order before the final Payment Application is submitted

## Slide 13: Contract vs. PO
If you’re not sure, ask Contracts!
For Contract:
  All Design and Construction need to be a Contract.
  Any item that has signed/sealed drawings or documents.
  High Risk items (equipment, etc.) noted below.
  Anything that results in a document that will be used in a construction, design, or other project.
For PO:
  Maintenance, Service Agreements, Commodities, and Replacement in Kind
Notes: SSJs for PO’s are on DFA’s website, different from one used for Contracts

## Slide 14: SUCF/Campus Let
New legislation that anything over $60k goes to the State
  OSC now has up to 75 calendar days to review documents as opposed to 30 calendar days previously
Consultant RFQ/RFP process
  Contracts needs to send out a formal Letter of Intent to selected Consultant
  The solicitation process is in effect until Contract Award
  PM to work with Contracts to negotiate Consultant fees
Updated checklists and guidance documents to come

## Slide 15: General
Always check the comments!
  Check your queue and email for Request Comments
A new General Conditions template for PWR projects is in eBuilder Resources Endowed folder
Please use the templates in eB Resources as they are the most up to date
Emails should be sent to the FC mailbox and copy the person you are working with

## Slide 16: Questions?