## Slide 1: Facilities Contracts
Change Order/PCO
Requirements
June 2024

## Slide 2: Required Backup
How the work was requested needs to be a clear and concise explanation.
Always attach the Contractors Change Order Request form (COR)
All relevant BA/ASI/RFI/emails/etc. need to be attached to the PCO process.
When requesting work verbally a confirmation email should be sent to vendor to confirm.

## Slide 3: Justification vs. Description of Work
Justification section:
  Describe what work was performed clearly referencing any BA/ASI/etc.
  It should answer “Why did we have to do this?”
Change Order Description:
  This language becomes part of the Contract via the CO.
  Be clear – What is being done and how? Add location area and directive, “per ASI/BA, Owner, etc.”
Notes: Change Order Description samples in eBuilder Resources under PCO

## Slide 4: Review your PCO’s
Double check dollar value
  The COR should have been reviewed for accuracy (OH&P, Bond, etc.) and matches eBuilder amount
    OH&P should not exceed 25% total per COR
Make sure COR form is filled out & all required backup is attached for both Prime and Subs.
Provide an updated Completion date, if applicable
  Campus Let Projects need to have this in the PCO and a justification memo is required.
Notes: There is an OH&P Calculation Worksheet in the checklists

## Slide 5: Reminders
Use the Comments Tab to advise Contracts of any additional information
Check your email and queue for any Request Comments
All Allowances need to be reconciled by the end of the Project via CO
Please limit CO’s to ten PCO’s and under

## Slide 6: Questions?