## Slide 1: Summer Construction Update
May 28, 2026

## Slide 2
Scale of Summer Work
58 projects: < $500K
32 projects: $500K - $2M
20 projects: $2M - $5M
15 projects: > $5M
~ 125 Projects @ $574M Project Cost
~ peak $20M per month in construction billings

## Slide 3
2022
2023
2024
2025
2026
2027
2028
SIBLEY DOME RENOVATION ($17.6M)
Aug ‘23 - Nov ‘23
Mar ‘24 - Jun ‘26
2029
2030
NEW EXP. HALL FOR CHESS ($28M)
Mar ‘22 - Dec ‘23
Jan ‘24 - Jan ‘25
ATKINSON HALL ($87.9M)
Apr ‘22 - Apr ‘25
OLIN LIBRARY RENO - McGraw ($22.1M)
Jan ‘23 – Sep ‘23
Dec ’23 - Mar ‘25
HUGHES HALL ENV REPLACE ($15M)
May ‘23 - Apr ‘26
Jan ‘23
BALCH HALL RENOVATION ($89M)
Mar ‘22 - Jul ‘24
Aug ‘25
CIS BUILDING ($113M)
Feb ‘23 – May ‘25
.
Nov ‘22
FIELD HOCKEY CLUBHOUSE ($11.3M)
Mar - Jul ‘27
Aug ‘23 - Dec ‘25
MEINIG FIELDHOUSE ($53.7M)
Aug ‘23 - July ‘24
Nov ‘24 - Aug ‘26
PLANT SCIENCE PHASE I ($69M)
Mar ‘22 - May ‘26
Dec ‘22
PLANT SCIENCE PHASE II ($74)
GENEVA FOOD RESEARCH LAB RENO ($30M)
KING-SHAW RENOVATION ($11M)
Feb ‘24 - Feb ‘25
May ‘25 - Jan ‘27
RICE HALL RENOVATION ($26M)
TMCF RENOVATION ($10M)
McGRAW HALL RENOVATION ($108.5M)
Jan ‘25 - Jan ‘28
Jan ‘23 - Aug ‘24
DUFFIELD HALL EXPANSION ($88.3M)
Sep ‘23 - Feb ‘25
Jan ‘25 - Apr ‘28
BB HALL MAKER SPACE ($11M)
Capital Program - Projects > $10M (CCF Projects in Green)
Feb ‘24 - Feb ‘25
May ‘25 - Mar‘ 27
AHDC EXPANSION ($30M)
CARPENTER ADDITON ($35M)
LIFE SCIENCES PAVILION ($22M)
Feb ‘24 - Apr ‘27
Feb ‘24 - Feb ‘25

## Slide 4
2022
2023
2024
2025
2026
2027
2028
SIBLEY DOME RENOVATION ($17.6M)
Aug ‘23 - Nov ‘23
Mar ‘24 - Jun ‘26
2029
2030
NEW EXP. HALL FOR CHESS ($28M)
Mar ‘22 - Dec ‘23
Jan ‘24 - Jan ‘25
ATKINSON HALL ($87.9M)
Apr ‘22 - Apr ‘25
OLIN LIBRARY RENO - McGraw ($22.1M)
Jan ‘23 – Sep ‘23
Dec ’23 - Mar ‘25
HUGHES HALL ENV REPLACE ($15M)
May ‘23 - Apr ‘26
Jan ‘23
BALCH HALL RENOVATION ($89M)
Mar ‘22 - Jul ‘24
Aug ‘25
CIS BUILDING ($113M)
Feb ‘23 – May ‘25
.
Nov ‘22
FIELD HOCKEY CLUBHOUSE ($11.3M)
Mar - Jul ‘27
Aug ‘23 - Dec ‘25
MEINIG FIELDHOUSE ($53.7M)
Aug ‘23 - July ‘24
Nov ‘24 - June ‘26
PLANT SCIENCE PHASE I ($69M)
Mar ‘22 - May ‘26
Dec ‘22
PLANT SCIENCE PHASE II ($74)
GENEVA FOOD RESEARCH LAB RENO ($30M)
KING-SHAW RENOVATION ($11M)
Feb ‘24 - Feb ‘25
May ‘25 - Jan ‘27
RICE HALL RENOVATION ($26M)
TMCF RENOVATION ($10M)
McGRAW HALL RENOVATION ($108.5M)
Jan ‘25 - Jan ‘28
Jan ‘23 - Aug ‘24
DUFFIELD HALL EXPANSION ($88.3M)
Sep ‘23 - Feb ‘25
Jan ‘25 - Apr ‘28
BB HALL MAKER SPACE ($11M)
Capital Program - Projects > $10M (CCF Projects in Green)
Feb ‘24 - Feb ‘25
May ‘25 - Mar‘ 27
AHDC EXPANSION ($30M)
CARPENTER ADDITON ($35M)
LIFE SCIENCES PAVILION ($22M)
Feb ‘24 - Apr ‘27
Feb ‘24 - Feb ‘25
5 projects @ $340M Warranty & Closeout

## Slide 5
2022
2023
2024
2025
2026
2027
2028
SIBLEY DOME RENOVATION ($17.6M)
Aug ‘23 - Nov ‘23
Mar ‘24 - Jun ‘26
2029
2030
NEW EXP. HALL FOR CHESS ($28M)
Mar ‘22 - Dec ‘23
Jan ‘24 - Jan ‘25
ATKINSON HALL ($87.9M)
Apr ‘22 - Apr ‘25
OLIN LIBRARY RENO - McGraw ($22.1M)
Jan ‘23 – Sep ‘23
Dec ’23 - Mar ‘25
HUGHES HALL ENV REPLACE ($15M)
May ‘23 - Apr ‘26
Jan ‘23
BALCH HALL RENOVATION ($89M)
Mar ‘22 - Jul ‘24
Aug ‘25
CIS BUILDING ($113M)
Feb ‘23 – May ‘25
.
Nov ‘22
FIELD HOCKEY CLUBHOUSE ($11.3M)
Mar - Jul ‘27
Aug ‘23 - Dec ‘25
MEINIG FIELDHOUSE ($53.7M)
Aug ‘23 - July ‘24
Nov ‘24 - June ‘26
PLANT SCIENCE PHASE I ($69M)
Mar ‘22 - May ‘26
Dec ‘22
PLANT SCIENCE PHASE II ($74)
GENEVA FOOD RESEARCH LAB RENO ($30M)
KING-SHAW RENOVATION ($11M)
Feb ‘24 - Feb ‘25
May ‘25 - Jan ‘27
RICE HALL RENOVATION ($26M)
TMCF RENOVATION ($10M)
McGRAW HALL RENOVATION ($108.5M)
Jan ‘25 - Jan ‘28
Jan ‘23 - Aug ‘24
DUFFIELD HALL EXPANSION ($88.3M)
Sep ‘23 - Feb ‘25
Jan ‘25 - Apr ‘28
BB HALL MAKER SPACE ($11M)
Capital Program - Projects > $10M (CCF Projects in Green)
Feb ‘24 - Feb ‘25
May ‘25 - Mar‘ 27
AHDC EXPANSION ($30M)
CARPENTER ADDITON ($35M)
LIFE SCIENCES PAVILION ($22M)
Feb ‘24 - Apr ‘27
Feb ‘24 - Feb ‘25
4 projects @ $152M
Recently Completed

## Slide 6
2022
2023
2024
2025
2026
2027
2028
SIBLEY DOME RENOVATION ($17.6M)
Aug ‘23 - Nov ‘23
Mar ‘24 - Jun ‘26
2029
2030
NEW EXP. HALL FOR CHESS ($28M)
Mar ‘22 - Dec ‘23
Jan ‘24 - Jan ‘25
ATKINSON HALL ($87.9M)
Apr ‘22 - Apr ‘25
OLIN LIBRARY RENO - McGraw ($22.1M)
Jan ‘23 – Sep ‘23
Dec ’23 - Mar ‘25
HUGHES HALL ENV REPLACE ($15M)
May ‘23 - Apr ‘26
Jan ‘23
BALCH HALL RENOVATION ($89M)
Mar ‘22 - Jul ‘24
Aug ‘25
CIS BUILDING ($113M)
Feb ‘23 – May ‘25
.
Nov ‘22
FIELD HOCKEY CLUBHOUSE ($11.3M)
Mar - Jul ‘27
Aug ‘23 - Dec ‘25
MEINIG FIELDHOUSE ($53.7M)
Aug ‘23 - July ‘24
Nov ‘24 - June ‘26
PLANT SCIENCE PHASE I ($69M)
Mar ‘22 - May ‘26
Dec ‘22
PLANT SCIENCE PHASE II ($74)
GENEVA FOOD RESEARCH LAB RENO ($30M)
KING-SHAW RENOVATION ($11M)
Feb ‘24 - Feb ‘25
May ‘25 - Jan ‘27
RICE HALL RENOVATION ($26M)
TMCF RENOVATION ($10M)
McGRAW HALL RENOVATION ($108.5M)
Jan ‘25 - Jan ‘28
Jan ‘23 - Aug ‘24
DUFFIELD HALL EXPANSION ($88.3M)
Sep ‘23 - Feb ‘25
Jan ‘25 - Apr ‘28
BB HALL MAKER SPACE ($11M)
Capital Program - Projects > $10M (CCF Projects in Green)
Feb ‘24 - Feb ‘25
May ‘25 - Mar‘ 27
AHDC EXPANSION ($30M)
CARPENTER ADDITON ($35M)
LIFE SCIENCES PAVILION ($22M)
Feb ‘24 - Apr ‘27
Feb ‘24 - Feb ‘25
6 projects @ $356M
In Construction

## Slide 7
2022
2023
2024
2025
2026
2027
2028
SIBLEY DOME RENOVATION ($17.6M)
Aug ‘23 - Nov ‘23
Mar ‘24 - Jun ‘26
2029
2030
NEW EXP. HALL FOR CHESS ($28M)
Mar ‘22 - Dec ‘23
Jan ‘24 - Jan ‘25
ATKINSON HALL ($87.9M)
Apr ‘22 - Apr ‘25
OLIN LIBRARY RENO - McGraw ($22.1M)
Jan ‘23 – Sep ‘23
Dec ’23 - Mar ‘25
HUGHES HALL ENV REPLACE ($15M)
May ‘23 - Apr ‘26
Jan ‘23
BALCH HALL RENOVATION ($89M)
Mar ‘22 - Jul ‘24
Aug ‘25
CIS BUILDING ($113M)
Feb ‘23 – May ‘25
.
Nov ‘22
FIELD HOCKEY CLUBHOUSE ($11.3M)
Mar - Jul ‘27
Aug ‘23 - Dec ‘25
MEINIG FIELDHOUSE ($53.7M)
Aug ‘23 - July ‘24
Nov ‘24 - June ‘26
PLANT SCIENCE PHASE I ($69M)
Mar ‘22 - May ‘26
Dec ‘22
PLANT SCIENCE PHASE II ($74)
GENEVA FOOD RESEARCH LAB RENO ($30M)
KING-SHAW RENOVATION ($11M)
Feb ‘24 - Feb ‘25
May ‘25 - Jan ‘27
RICE HALL RENOVATION ($26M)
TMCF RENOVATION ($10M)
McGRAW HALL RENOVATION ($108.5M)
Jan ‘25 - Jan ‘28
Jan ‘23 - Aug ‘24
DUFFIELD HALL EXPANSION ($88.3M)
Sep ‘23 - Feb ‘25
Jan ‘25 - Apr ‘28
BB HALL MAKER SPACE ($11M)
Capital Program - Projects > $10M (CCF Projects in Green)
Feb ‘24 - Feb ‘25
May ‘25 - Mar‘ 27
AHDC EXPANSION ($30M)
CARPENTER ADDITON ($35M)
LIFE SCIENCES PAVILION ($22M)
Feb ‘24 - Apr ‘27
Feb ‘24 - Feb ‘25
6 Projects
in Design

## Slide 8: Summer Operations GIS Map
https://cornell.maps.arcgis.com/apps/webappviewer/index.html?id=e7eb8bb4a2b0459c8208f3d44612c6fe
Notes: 114 projects in construction
$838 M in total project cost

## Slide 9
Major Roadwork & Paving
Hollister Drive and Lot Paving & Sidewalks
Cradit Farm Drive Paving & Sidewalks
Large Animal Research Lot Paving
Olin Hall Accessibility
Campus/Garden Water Service

## Slide 10
Building Envelope & Roofing
Corson/Mudd
Roof
VMC Roof
Clara Dickson
Roof
George Jameson and HR5 Storefronts

## Slide 11
Arts Quad and West Campus Area
Arts Quad
Site Lighting
Sibley Stairs
McGraw Hall
Arts Quad
Duct Bank
West Campus Generator Expansion
Baker Tunnel HW
Gothic Chimney Repairs
WSH Generator

## Slide 12
Large Capital Projects
Life Sciences Pavilion
Rice Hall
Meinig Field House
King Shaw
McGraw Hall
GFR FH Clubhouse
Duffield Hall
Expansion

## Slide 13
Construction Phase - Communication
“The single biggest problem in communication is the illusion that it has taken place.” - George Bernard Shaw
  Please Err on the side of over communicating but…be clear and concise
  Think early and often about the local and campus wide impact of your project (update Trimble project construction impacts statement)
  Use a layered approach targeted for each type of audience
    “Success with Constant Contact bi-weekly project updates for impactful projects”
  Don’t forget your third-party consultants (FM Global, Commissioning Agents, Testing agents etc…)
  Every project should have a project communication plan/strategy in place…that has been shared and vetted with partners and stakeholders

## Slide 14
Questions?