## Slide 1: Working with the Cornell Shop Staff
Erik Gray
Zone Facility Director, SCL-Zone
eeg4 / 5-1120
UFR-PM-MM-MP-ZFD

## Slide 2: Then & Now... What’s Changed?
  Bain: Move from construction... to maintenance focus.
  Growing to meet work demand verses core mission
    Pre-2008 400+ FTE verses 221 FTE
  Flat Maintenance Budgets = delays in work
  Zone Implementation

## Slide 6: FM Planning & Scheduling update

## Slide 7: Current Pilot:
51 trades staff scheduled regularly (20%)
1.8 FTE’s
Schedules produced on a weekly basis (confirming materials are in-hand, shutdowns and access pre-arranged).
Compliance/safety items, SR priority, age of request, geographic location.

## Slide 8: Pilot Results:
In SCL-Zone 24 staff scheduled by one FTE
  Executed same number of CM/PM service requests, but with two fewer FTE’s.
  Work was accomplished 11% faster.
  Customer Surveys: ratings of “Timeliness” increased 18%

## Slide 9: What now? Pilot, to roll out...
Manager of Planning & Scheduling
Widespread internal review (pitfalls, successes, opportunities, and ROI metrics).
Identify dedicated resources
Procurement interface

## Slide 10: Timeline for the next stage...
Present – Nov ‘18: Finish internal review, solidify dedicated resources, finalize rollout of specific new areas to begin. Review plan with unit partners.
Dec ‘18 –Spring ‘19: Socialize, train and implement scheduling in new areas.
Summer ‘19: Review ROI, adjust accordingly.

## Slide 11
Marathon, not a sprint
Transformative

## Slide 12: We’re here to help!
Emergency response
Planned project support.
  Can staff up, with enough notice to get temps from downtown (ECI). 3-4 week lead.
  Project Support (access holes, system shutdowns, final cleaning, etc...).

## Slide 13
The fine print: What to keep in mind when asking us for help
Plan ahead, so we can plan. People aren’t sitting on a bench waiting for work.
We aren’t right for every job. Contact us and ask!
-FCS website
-Zone Director, Maintenance Planner, Zone Facilities Manager
We are NOT trying to grow our “business”... and our maintenance core mission must come FIRST.